## Cover
An illustration of the application of Failure Modes and Effects Analysis (FMEA) techniques to the analysis of information security risks
Introduction and acknowledgement
The original version of this spreadsheet was kindly provided to the ISO27k Implementers' Forum by Bala Ramanan to demonstrate how the FMEA method can be used to analyze information security risks. Subsequently, Bala kindly agreed to donate it to the ISO27k Toolkit. Apart from minor updates and reformatting, it is essentially unchanged. We are very grateful for Bala's input.
Contents
The FMEA Sample tab has the actual illustration - an analysis of possible failure modes for a firewall.
The Guidelines provide additional notes on the FMEA method, including a step-by-step process outline.
The Severity, Probability and Detectability tabs have tables demonstrating scales commonly used to rank risks by these criteria.
Copyright
This work is copyright © 2008, ISO27k Forum, some rights reserved. It is licensed under the Creative Commons Attribution-Noncommercial-Share Alike 3.0 License. You are welcome to reproduce, circulate, use and create derivative works from this provided that (a) it is not sold or incorporated into a commercial product, (b) it is properly attributed to the ISO27k Implementers’ Forum at www.ISO27001security.com, and (c) derivative works are shared under the same terms as this.
Disclaimer
Risk analysis is more art than science. Don't be fooled by the numbers and formulae: the results are heavily influenced by the accuracy of the users' assessment of risk factors, by the definition of information assets and by the framing of risks being considered. For these reasons, the process is best conducted by a team of people with solid expertise and practical experience of (a) assessing and managing information security risks, and (b) the organization, its internal and external situation with respect to information security. Don't expect to get definitive answers from anyone. It is impossible to guarantee that all risks have been considered and analyzed correctly. Some very experienced practitioners in this field claim that all risk analysis is basically bunkum, and we have some sympathy with that viewpoint.
The results of the analysis should certainly be reviewed by management (ideally including IT auditors, Legal, HR, other support functions and/or information security consultants) and may be adjusted according to their experience, so long as the expert views are taken into consideration. Remember: just because the organization has little if any experience of a particular informaiton security risk does not necessarily mean that it can be discounted. Organizations with immature security management processes and systems may have significant ongoing security incidents that are not even recognized, due to inadequate incident detection and reporting processes.

## Guidelines
Guideline to Carry out a Risk Assessment Using FMEA
Important notes:
This method does not consider asset values. Rrisks are identified for each asset and prioritized without taking account of the asset values.
The Cumulative risk for the identified asset for each threat is ascertained by the Risk Priority Number (RPN)
Each asset can have more than one failure mode and for each failure mode there can be more than one vulnerability
How to carry out the Risk Assessment (RA) using FMEA:
1 | Identify the assets or the services rendered by the department under the scope of RA
5 | Now identify the failure modes for the identified asset/function. Please note that there could be more than one vulnerabilities for each asset
6 | Now identify the impact if the identified failure mode happens. That if the identified failure mode happens what will be the effect on the business or service.
7 | Now refer the impact chart and choose the number relevant to the effect of the failure mode
8 | Now identfiy the cause for the failure mode. Please note that each vulnerability can be linked with more than one threat.
9 | Now refer to the probability chart and choose the number that is more relevant to the frequency of the threat happening.
10 | Now list down the current controls. Kindly categorize the controls as preventive and detective controls. Write each control in separate rows.
11 | Now refer to the vulnerability chart and choose a number relevant to the size of vulnerability for each asset and the effectiveness of the controls that might have.
12 | Input all three in the corresponding fields. You can now see the Risk Priority Number calculated for a failure mode of the respective asset function.
13 | Now if the RPN is not under the acceptable value then the risk status shows "HIGH RISK", recommendation to mitigate each of these HIGH RISK has to be listed down. Kinldy list each control in separate rows.
Using prioritized risks
Management may decide to target, say, the top 5% of risks initially. This is an arbitrary value that can be reviewed/adjusted later.
Following the FMEA method, the risks are assessed, RPNs calculated and then risks are ranked by RPN.
5% of 1000 (the maximum RPN value) is 50. So any RPN above 50 requires review and (probably) control improvements.
All risks with RPNs above 50 are identified as "HIGH RISK". This criterion is of course based on the arbitrary 5% value noted above.
If the organization is well controlled with relatively few HIGH RISK items, the 5% value may be extended to, say 15% to address lower risks.
Alternatively, if there are simply too many HIGH RISK items to tackle at once, they may be addressed in top-down sequence according to the RPNs.
The prioritized list of risks provides management with a rational basis for determining how much resource to apply to risk reduction: the cutoff point should go further down the list if more resources are allocated, and vice versa.

## FMEA Sample
A/A | Asset Name | Function | Potential Vulnerability | Potential Threat | Potential Business Consequence (Impact) | Impact | Likelihood | Current Controls |  | Vulnerability | RPN
[8 empty] | Preventive Controls | Detective Controls
1 | Domain Controller / File Server | 1)Verifies users on computer network. 2)Stores industry data (high value non personal data) | Rules not appropriately configured | Excessive Privilege Abuse | Inability to verify users on the network. Inability to access data | 10 | 8 | Strict and grant database access base on the user roles requirements |  | 5 | 400
2 |  |  | Operating system doesn't support security updates | Threats and viruses created after 01/2020 | Attacker gains control, file system is destroyed | 8 | 5 | Antivirus program | Antivirus program | 6 | 240
3 | Industry Employee Data | Employees information | Database not encrypted | Insider Employee gets employee personal data | Disclosure or modification of personal information | 8 | 6 | Internal Employee Rules and Procedures available | Log Monitoring | 7 | 336
4 | Edge-Router | packet filtering , routing packages | incomplete package sender authentication | access to the network of unauthorized user | non authorised users send or receive confidential data | 8 | 4 | Mandatory Access Control, Firewall | Log Monitoring | 4 | 128
5 |  |  | no prevention of big incoming packet flows | receiving many packets at once, router buffers are full (DoS/DDoS) | router is blocked, it stops transmitting packets | 8 | 5 | NAT is enabled, Disconnect from the Internet, Firewall | Network traffic monitoring software | 6 | 240
6 | Router 1-4 | connecting VLANS, routing packages | hard coded password hashes | malicious user with access to a network device gets access to the whole network with admin rights | data theft, attacker monitors the network traffic | 8 | 4 | Firewall | RADIUS AAA, Log Monitoring | 4 | 128
7 |  |  | non-encrypted frames of CDP protocol | unauthorised user gets access to the CDP frames content | Attacker gains information about the network topology and all network vulnerabilities, can attack any device | 7 | 5 | Firewall | Log Monitoring | 6 | 210
8 | Switch 4.1,4.2 | connecting the servers, packet switching | Default port used to create trunk links | Switch spoofing | VLAN hopping (attacker gets access to other VLANs) | 7 | 5 | RADIUS AAA |  | 6 | 210
9 | Switch 1 Switch 2 Switch 3 | connecting devices in a VLAN, packet switching | CAM table has limited MAC addresses, lack of configuration regarding MAC addresses | MAC flooding attack | Attacker tracks the VLAN traffic, switch stops working, switch remains vulnerable to other attacks | 8 | 4 |  | Network traffic monitoring software, RADIUS AAA | 6 | 192
10 | RADIUS/SNMP Server | user authentication, monitor users inside network | Use of non-secure MD5 hashing for keys | Unauthorised user gets the cryptographic key (shared secret) | Theft or modification of user passwords | 10 | 5 |  |  | 8 | 400
11 |  |  | Uses stateless and connectionless protocol (UDP) | Packet spoofing | Leak of network information | 7 | 6 |  | Log Monitoring | 6 | 252
12 | DNS/DHCP Server | assigning IP addresses and names to devices | 1) Insufficient configuration 2) DNS protocol vulnerabilities | Cache poisoning DNS Spoofing (MITM) | data theft, server crashes, network services stop working | 8 | 7 |  | Log Monitoring, RADIUS AAA | 6 | 336
13 | Industry Customer Data | Customer information | Execute SQL queries with no control | SQL Injection attack | Disclosure or modification of personal information | 8 | 6 | Limited freeform user input | Log Monitoring | 6 | 288
14 | CRM Server | customer-bussiness interaction, local sales automation | No user verification | Unauthorised access in processes | Fake order placement, transaction delays, disclosure and modification of data | 8 | 4 | Internal Employee Rules and Procedures available | Log Monitoring | 6 | 192
15 | Application Server | customer-bussiness interaction, remote sales automation | 1) Receives HTTP requests from non verified sources 2) Allocates memory for connections before the TCP 3-way handshake is completed | DoS/ Distributed DoS - TCP SYN/UDP Flood Attacks | Loss of funcionality, services denied to authorised users (customers) | 10 | 8 | Disconnect from the Internet | Network traffic monitoring software | 6 | 480
16 |  |  | Uncontrolled software installation | Unneeded/ unverified software runs on the server | Unwanted network traffic, more ways for hackers to crack the system | 6 | 8 |  | Log Monitoring | 7 | 336
17 | Windows 7 | PC operating system | Microsoft doesn't release security patches since 01/2020 | All threats created since 01/2020 | Data theft, device loss of functionality | 8 | 5 | Antivirus program | Antivirus program | 6 | 240
18 | Create New Customer | The process of creating a new customer entry in the database, is executed in Sales & IT PCs | 1) Insufficient configuration 2) No type checking in input fields | SQL Injection attack | Unauthorised access or modification of data | 8 | 5 | Limited freeform user input | Log Monitoring | 5 | 200
19 | Create New Order(Local) | The process of creating a new order locally, on the Sales & IT PCs | Staff has access to all sales data via the process | Insider employee leaks sales data | Leak of sensitive data like bank accounts, statistics, customer data etc | 7 | 4 | Internal Employee Rules available | Log Monitoring | 7 | 196
20 | Create New Order(Remote) | The process of creating a new order remotely, is executed in the Application Server | Bad implementation of user authentication and session management | Attackers gain access to user accounts | Leak of customer data, fake order creation | 7 | 7 |  | Log Monitoring | 6 | 294
21 | Customer Support | The customer support process, is executed in the Accounting & HR PCs | 1) Proper customer support requires sensitive personal data 2) The process has access to all customer data with no filter | Insider employee leaks sales data | Leak of sensitive data (bank accounts, credit card numbers etc) | 7 | 4 | Internal Employee Rules available | Log Monitoring | 7 | 196
22 | PC 1-2 PC 3-6 | Accounting & HR workstations, execute customer support process Sales & IT workstations, execute customer and local order creation processes | 1) BIOS are erasable, no access control in BIOS 2) Many PCs in a VLAN | BIOS attacks (ex. BIOS rookit) | Attacker gains full control of the PC and access to the VLAN | 10 | 7 | Self healing BIOS |  | 6 | 420
23 |  |  | Weak password | Unauthorised user gains access to the PC | Unauthorised user modifies/ deletes /destroys data | 7 | 4 |  | Log Monitoring | 6 | 168
24 |  |  | Employees are not informed of potential threats in the Internet | 1) Unauthorised software installation 2) Social engineering attacks, worms, fraud | Malicious software steals data | 6 | 7 | Antivirus program | Antivirus program | 5 | 210
25 | Email Server | mail exchange management | weak authentication techniques | mail user password cracking | Attacker gains access to personal data | 7 | 5 | RADIUS AAA |  | 6 | 210
26 |  |  | no load balance for incoming packets | DoS/DDoS attack | Unwanted network traffic, Email server stops working | 8 | 6 | Disconnect from the Internet | Network traffic monitoring software, RADIUS AAA | 6 | 288
27 | WLAN Controller | access point management, allows or declines connections | 1) The software runs code in memory with no bounds check 2) Bugs in frame processing | Buffer overflow | 1) Access in sensitive information, data leak 2) Wireless network malfunctions/ delays/ stops working | 9 | 5 |  | Log Monitoring | 7 | 315
28 | Access Point | allows wireless devices to connect to the wired network | Improper resource management while processing UDP packets | UDP flood attack | Connected devices are temporarily disconnected | 8 | 5 | Disconnect from the Internet | Network traffic monitoring software, RADIUS AAA | 5 | 200
29 |  |  | Improper handling of clients connection requests | Unauthorised user sends multiple authentication requests (DDoS) | Networks stops working temporarily | 8 | 6 | Disconnect from the Internet | Network traffic monitoring software, RADIUS AAA | 6 | 288
30 |  |  | Wireless channels interference | User connected to a nearby wireless network interferes to the local WLAN traffic | Unauthorised access to frames in the network | 7 | 4 | enabled interferer detection service during the set up of the WLAN |  | 6 | 168
31 | Laptop | Director's personal computer | Weak password | Unauthorised user gets access to the Laptop | Unauthorised access or modification of data | 7 | 4 |  | Log Monitoring | 6 | 168
32 |  |  | Connected in wireless network, automated connection to the first available access point | Fake access point attack | Credentials, logins and passwords theft | 7 | 2 |  |  | 7 | 98
33 |  |  | Is portable device | Theft | Data stored in the device are stolen | 9 | 4 |  | Security guard | 4 | 144
34 | VoIP Phone | make calls through the Internet | Data transmited in a non encrypted format | Eavesdropping | Leak of conversations, use of information in future attacks | 7 | 5 |  | Log Monitoring | 7 | 245
35 |  |  | Default passwords | Interference from malicious user | Leak of sensitive data, delay in calls | 10 | 4 | Stop making calls and disconnect temporarily | Log Monitoring | 6 | 240
36 | Printer | print documents | 1) Transfer data in a non encrypted format 2) No access control to the printer via network | Malicious user/software interferes in transmission of data to be printed | Leak of sensitive data | 7 | 3 | RADIUS AAA |  | 5 | 105
37 | Tablet PC | Director's personal tablet, communicate with co-workers | Weak or non existent password | Easy to crack password | Personal data of the director are leaked | 7 | 4 |  |  | 6 | 168
38 |  |  | Connected in the same VLAN with important devices, and is easier to crack | Violation of the VLAN | Gain access to other important devices | 7 | 3 | Disconnect from the Internet, antivirus program | Antivirus program | 4 | 84
39 | HRM Server | employee management | Execute SQL queries with no control | SQL Injection attack | Disclosure or modification of employee performance information | 7 | 4 | Limited freeform user input | Log Monitoring | 4 | 112
40 |  |  | Improper authentication and verification of user privileges | Attacker gets access to employee performance data and new employee guidelines | 1) Disclosure or modification of employee performace data 2) Server malfunction (provides false guidelines) | 7 | 3 | RADIUS AAA | Log Monitoring | 4 | 84
41 | Windows 10 Pro | PC operating system | Newest update is not installed | Threats and viruses the OS provider has handled since the latest update | The PC running Windows 10 is not protected, data theft | 6 | 2 | Antivirus program (Windows Defender) | Antivirus program (Windows Defender) | 4 | 48
Note on C2: List down the fucntion or purpose of the asset. If more than one purpose is identified for the identified service list them down separately
Note on D2: In what all ways the service running on this asset can fail? ie the vulnerabilities List down each failure mode separately
Note on E2: if the vulnerability happens, then what could be the effect of the failure? If there is more than one failure list them seperately
Note on G2: Refer Severity Table
Note on H2: Refer Probabilty Table
Note on I2: Identify the current controls vis a vis preventive and detective controls. If there are more than one, then list them separately
Note on K2: Refer Detection table

## Impact
Effect | Impact of Threat realisation | Ranking
Catastrophic | Resource not available / Problem unknown | 10
Extreme | Resource not available / Problem known and cannot be controlled | 9
Very High | Resource not available / Problem known and can be controlled | 8
High | Resource Available / Major violation of policies | 7
Moderate | Resource Available / Major violations of process | 6
Low | Resource Available / Major violations of procedures | 5
Very Low | Resource Available / Minor violations of policies | 4
Minor | Resource Available / Minor violations of process | 3
Very Minor | Resource Available / Minor violations of procedures | 2
None | No effect | 1

## Likelihood
PROBABILITY of Failure | Failure Prob | Ranking
Very High: Threat is almost inevitable | >1 in 2 | 10
| 1 in 3 | 9
High: Repeated Threat occurences | 1 in 8 | 8
| 1 in 20 | 7
Moderate: Occasional Threat occurences | 1 in 80 | 6
| 1 in 400 | 5
| 1 in 2,000 | 4
Low: Relatively few Threat occurences | 1 in 15,000 | 3
| 1 in 150,000 | 2
Remote: Threat occurence is unlikely | <1 in 1,500,000 | 1

## Vulnerability
Vulnerability | Ranking
The vulnerability is very exposed and directly, remotely exploitable, and its exploitation could result in severe impacts. Relevant security control or other remediation is not implemented and not planned; or no security measure can be identified to remediate the vulnerability. | 10
The vulnerability is exposed and exploitable, and its exploitation could result in severe impacts. Relevant security control or other remediation is not implemented and not planned; or no security measure can be identified to remediate the vulnerability. | 9
The vulnerability is of very high concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is planned but not implemented | 8
The vulnerability is of high concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is planned but not implemented | 7
The vulnerability is of moderate concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is partially implemented and somewhat effective. | 6
The vulnerability is of moderate concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is implemented and effective. | 5
The vulnerability is of minor concern, but effectiveness of remediation could be improved. Relevant security control or other remediation is fully implemented and somewhat effective | 4
The vulnerability is of minor concern, but effectiveness of remediation could be improved. Relevant security control or other remediation is fully implemented and effective | 3
The vulnerability is not of concern. Relevant security control or other remediation is fully implemented, assessed, and effective | 2
There is no vulenrability | 1